## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) Number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA-01 | Register new account | As a TA, I want to register a new account using my student ID, so that I can access the recruitment system. | Must Have | 1 | - Student ID must be unique in system. - User sets a password with minimum 8 characters. - Registration success redirects to login page. - Duplicate registration shows error message. | 2 | Authentication foundation. | 2026-03-23 | 2026-04-05
TA-02 | Login to system | As a TA, I want to log in with my credentials, so that I can access my personal dashboard. | Must Have | 1 | - Login requires Student ID and password. - Incorrect credentials display error message. - Successful Login redirects to TA dashboard. - Session persists until logout. | 2 | Security baseline. | 2026-03-23 | 2026-04-05
TA-03 | Edit personal information | As a TA, I want to update my personal information (email, phone, major), so that my profile stays current. | Must Have | 1 | - User can modify email, phone number, and major. - Changes are saved to file and persist after logout. - Student ID and name cannot be changed after registration. | 2 | Profile management. | 2026-03-23 | 2026-04-05
TA-04 | Upload profile photo | As a TA, I want to upload a profile photo, so that MOs can recognize me. | Should Have | 2 | - Supports JPG and PNG formats. - Image size limited to 2MB. - Photo displayed on profile and applications. - User can replace or remove photo. | 2 | Optional visual feature. | 2026-04-06 | 2026-04-19
TA-05 | Browse job categories | As a TA, I want to browse jobs by category (e.g., Programming, Marking, Lab Assistant), so that I can find roles matching my interest. | Must Have | 1 | - Jobs are categorized by type. - User can click a category to view all Jobs in that category. - category list is predefined by system. | 3 | Better job discovery. | 2026-03-23 | 2026-04-05
TA-06 | Save jobs to wishlist | As a TA, I want to save interesting jobs to a wishlist, so that I can apply later without searching again. | Could Have | 2 | - User can click "Save" button on any job. - Saved jobs appear in a separate "Wishlist" tab. - User can remove jobs from wishlist. - Applying removes job from wishlist automatically. | 3 | User convenience. | 2026-04-06 | 2026-04-19
TA-07 | Submit application with cover letter | As a TA, I want to submit a cover letter along with my application, so that I can explain why I am suitable for the role. | Must Have | 2 | - Application form includes a text area for cover letter. - Cover letter is saved with application record. - MO can view cover letter when reviewing applications. - Cover letter is optional. | 2 | Additional context for MO. | 2026-04-06 | 2026-04-19
TA-08 | Cancel application before deadline | As a TA, I want to cancel my application before the job deadline, so that I can change my mind if needed. | Should Have | 2 | - Cancel option available only before job deadline. - Canceled application is removed from MO's review list. - User receives confirmation of cancellation. - User can reapply before deadline if desired. | 3 | Flexibility for applicants. | 2026-04-06 | 2026-04-19
TA-09 | View application history | As a TA, I want to view my complete application history from all semesters, so that I can track my past applications. | Should Have | 3 | - History shows all applications across semesters. - Each entry shows job title, semester, status, and final outcome. - Filter by semester available. - Archived records are read-only. | 3 | Long-term tracking. | 2026-04-20 | 2026-05-03
TA-10 | Receive in-app notifications | As a TA, I want to receive in-app notifications for status changes, so that I stay informed without checking email. | Must Have | 3 | - Bell icon shows unread notification count. - Notifications appear for: Application reviewed, shortlisted, rejected, offered, interview scheduled. - Clicking notification opens relevant page. - Notifications can be marked as read. | 3 | Real-time updates. | 2026-04-20 | 2026-05-03
TA-11 | Export my profile as PDF | As a TA, I want to export my profile and CV as a single PDF, so that I can share it externally if needed. | Could Have | 4 | - "Export Profile" button generates PDF. - PDF includes profile info, skills, CV content, and photo. - File saved to user's local system. | 3 | Extra utility feature. | 2026-05-04 | 2026-05-17
TA-12 | Receive skill gap suggestions | As a TA, I want the system to suggest courses or resources to fill skill gaps for jobs I'm interested in, so that I can improve my qualifications. | Could Have | 4 | - For each job, system lists missing skills. - Each missing skill links to recommended learning resource. - Suggestions are based on pre-defined mapping. - Feature is AI-assisted with explainability. | 5 | AI-powered development. | 2026-05-04 | 2026-05-17
MO-01 | Create module profile | As an MO, I want to create a profile for my module, so that I can manage TA recruitment for that module. | Must Have | 1 | - MO can add module code, name, department, and description. - One MO can manage multiple modules. - Module profile linked to all jobs posted for that module. | 3 | Organizational structure. | 2026-03-23 | 2026-04-05
MO-02 | Set application deadline | As an MO, I want to set an application deadline for each job, so that applications close automatically after that date. | Must Have | 1 | - Deadline field with date picker. - Jobs with passed deadline are not visible to TA for application. - MO can extend deadline before it passes. - Deadline displayed prominently to TA. | 2 | Time management. | 2026-03-23 | 2026-04-05
MO-03 | Duplicate previous job posting | As an MO, I want to duplicate a job posting from a previous semester, so that I don't have to re-enter all details. | Should Have | 2 | - "Duplicate" button on existing job. - Creates new job with same details but blank dates. - MO can modify before publishing. - Saves time for recurring jobs. | 3 | Efficiency feature. | 2026-04-06 | 2026-04-19
MO-04 | View applicant analytics | As an MO, I want to see analytics about applicants (e.g., number by major, average GPA), so that I understand the applicant pool. | Should Have | 3 | - Charts show distribution of applicants by major, year, and skill. - Data refreshes as new applications arrive. - Export analytics as CSV. - Aggregated data only, no individual identification. | 5 | Data-driven decisions. | 2026-04-20 | 2026-05-03
MO-05 | Add interview notes | As an MO, I want to add private interview notes for each applicant, so that I can remember details during evaluation. | Should Have | 3 | - Notes field visible only to MO who created them. - Notes saved with application record. - Can be edited multiple times. - Timestamp shows when notes were last updated. | 2 | Evaluation support. | 2026-04-20 | 2026-05-03
MO-06 | Batch update application status | As an MO, I want to update the status of multiple applicants at once, so that I can process many rejections efficiently. | Could Have | 4 | - Checkbox selection on applicant list. - Bulk action dropdown with status options. - Confirmation dialog before execution. - All selected applicants updated simultaneously. | 4 | Efficiency for high-volume roles. | 2026-05-04 | 2026-05-17
MO-07 | Request additional documents | As an MO, I want to request additional documents from shortlisted applicants, so that I can verify qualifications. | Should Have | 3 | - MO can send document request via system. - TA receives notification and can upload requested docs. - Request status shows pending/uploaded. - Document type (e.g., transcript, certificate) specified. | 4 | Verification workflow. | 2026-04-20 | 2026-05-03
MO-08 | Release job offer with terms | As an MO, I want to release a formal job offer with terms (hours, rate, duration), so that TA can accept or decline. | Must Have | 3 | - Offer includes weekly hours, pay rate, start date, end date. - TA receives offer notification. - TA can accept or decline with one click. - System records offer acceptance date. | 3 | Formal hiring. | 2026-04-20 | 2026-05-03
MO-09 | View AI candidate ranking | As an MO, I want to see AI-ranked candidate list based on skill match and academic performance, so that I can prioritize reviews. | Could Have | 4 | - Ranking algorithm considers skills, GPA, and experience. - Ranking displayed with score and justification. - MO can override ranking manually. - Explainability provided for AI recommendations. | 5 | AI-assisted screening. | 2026-05-04 | 2026-05-17
ADM-01 | Manage user accounts | As an Admin, I want to create, disable, or reset passwords for TA and MO accounts, so that I can maintain system access. | Must Have | 2 | - Admin can add new MO accounts. - Admin can disable TA/MO accounts. - Admin can reset passwords for any account. - All actions logged with timestamp and admin ID. | 5 | User management. | 2026-04-06 | 2026-04-19
ADM-02 | Configure system settings | As an Admin, I want to configure system settings (e.g., max TA workload hours, file size limits), so that the system adapts to school policies. | Should Have | 3 | - Admin can set max weekly workload per TA. - Admin can set max CV file size. - Admin can set allowed file types. - Settings persist after system restart. | 4 | System configuration. | 2026-04-20 | 2026-05-03
ADM-03 | Generate recruitment reports | As an Admin, I want to generate semester recruitment reports, so that I can analyze overall hiring trends. | Should Have | 3 | - Reports include: total jobs posted, applications received, hires made. - Filter by department, module, semester. - Export as PDF or CSV. - Summary statistics included. | 5 | Reporting feature. | 2026-04-20 | 2026-05-03
ADM-04 | Monitor system logs | As an Admin, I want to view system activity logs (logins, job postings, applications), so that I can audit usage. | Could Have | 4 | - Logs show timestamp, user ID, action type. - Search and filter by user or date range. - Logs are read-only. - Retention period configurable. | 4 | Audit and security. | 2026-05-04 | 2026-05-17
ADM-05 | Approve new MO accounts | As an Admin, I want to approve new MO account requests, so that only authorized faculty can post jobs. | Must Have | 2 | - MO registration requires admin approval. - Admin receives pending approval list. - Admin can approve or reject with reason. - Approved MO receives email notification. | 3 | Access control. | 2026-04-06 | 2026-04-19